## Cost Estimation
COST ESTIMATION AND BUDGETING
Loyalty Program Optimizer Agent Development Project
Category | Line Item | Quantity | Unit | Unit Cost (PKR) | Subtotal (PKR)
Labor Costs | Project Manager (Soban) | 240 | hours | 1500 | 360000
Labor Costs | ML/Backend Developer (Abdul Moeiz) | 320 | hours | 1200 | 384000
Labor Costs | API/Frontend Developer (Uzair) | 280 | hours | 1200 | 336000
Labor Costs | Testing & QA (All Members) | 120 | hours | 800 | 96000
Infrastructure & Tools | Development Workstations | 3 | units | 45000 | 135000
Infrastructure & Tools | Cloud Computing (AWS/Azure) | 1 | package | 35000 | 35000
Infrastructure & Tools | Development IDEs & Tools | 3 | licenses | 8000 | 24000
Infrastructure & Tools | Version Control (GitHub Pro) | 1 | subscription | 1500 | 1500
Infrastructure & Tools | Project Management Software | 1 | subscription | 3000 | 3000
Software Licenses | Python ML Libraries (Premium) | 1 | package | 15000 | 15000
Software Licenses | Database Management System | 1 | license | 12000 | 12000
Software Licenses | API Development Tools | 1 | toolkit | 8000 | 8000
Data & Cloud Services | Synthetic Dataset Generation | 1 | dataset | 5000 | 5000
Data & Cloud Services | Cloud Storage | 1 | package | 8000 | 8000
Data & Cloud Services | API Rate Limits & Services | 1 | package | 10000 | 10000
Testing & QA | Automated Testing Tools | 1 | license | 7000 | 7000
Testing & QA | Performance Testing Services | 1 | package | 12000 | 12000
Documentation & Training | Technical Documentation Tools | 1 | license | 4000 | 4000
Documentation & Training | Training Materials Development | 1 | set | 6000 | 6000
Miscellaneous | Stakeholder Meeting Costs | 10 | meetings | 1500 | 15000
Miscellaneous | Buffer for Unforeseen Expenses | 1 | lump sum | 25000 | 25000
|  |  |  | Total Direct Cost: | 1501500
|  |  |  | Contingency (15%): | 225225
|  |  |  | TOTAL BUDGET (BAC): | 1726725

## Earned Value Analysis
EARNED VALUE ANALYSIS
After 3 Months of Project Execution
PROJECT BASELINE
Total Budget (BAC) | 1726725 PKR
Planned Duration | 2.8 months
Time Elapsed | 3 months
ASSUMPTIONS AT 3-MONTH MARK
Planned % Complete | 90% | Based on schedule baseline
Actual % Work Complete | 75% | Behind schedule - testing delays
Actual % Budget Spent | 85% | Cost overrun - additional resources
EARNED VALUE METRICS
Planned Value (PV) | 1554052.5 PKR |  | Work that should have been completed
Earned Value (EV) | 1295043.75 PKR |  | Work actually completed
Actual Cost (AC) | 1467716.25 PKR |  | Costs actually incurred
VARIANCE ANALYSIS
Cost Variance (CV = EV - AC) | -172672.5 PKR |  | Negative = Over Budget
Schedule Variance (SV = EV - PV) | -259008.75 PKR |  | Negative = Behind Schedule
PERFORMANCE INDICES
Cost Performance Index (CPI = EV/AC) | 0.882 |  | Below 1.0 indicates cost overrun
Schedule Performance Index (SPI = EV/PV) | 0.833 |  | Below 1.0 indicates behind schedule
FORECASTS
Estimate at Completion (EAC = BAC/CPI) | 1956955 PKR |  | Projected total cost at completion
Budget Overrun (EAC - BAC) | 230230 PKR |  | Additional funds needed
New Estimated Duration (Duration/SPI) | 3.36 months |  | Projected completion time
Schedule Delay | 0.56 months |  | Additional time needed

## Interpretation
PROJECT EARNED VALUE INTERPRETATION
PROJECT STATUS INTERPRETATION (After 3 Months)
1. SCHEDULE PERFORMANCE
Schedule Variance (SV): -259,008.75 PKR (NEGATIVE)
Schedule Performance Index (SPI): 0.833 (BELOW 1.0)
INTERPRETATION: The project is BEHIND SCHEDULE.
- We planned to complete 90% of work by month 3
- We have actually completed only 75% of work
- The 15% shortfall indicates schedule delays
ROOT CAUSES:
- Integration testing took longer than estimated (4.3 API & Dashboard delays)
- Dependencies on external tools caused setup delays
- Team members had competing academic commitments
- ML model training required more iterations than planned
IMPACT: Based on current SPI, the project will take 3.36 months instead of 2.8 months -
a delay of approximately 0.56 months (17 days).
2. COST PERFORMANCE
Cost Variance (CV): -172,672.50 PKR (NEGATIVE)
Cost Performance Index (CPI): 0.882 (BELOW 1.0)
INTERPRETATION: The project is OVER BUDGET.
- We have completed 75% of work worth 1,295,043.75 PKR
- But we have spent 1,467,716.25 PKR (85% of total budget)
- We are spending approximately 13.3% more than planned for each unit of work
ROOT CAUSES:
- Additional cloud computing resources needed for ML model training
- Premium testing tools purchased that weren't in original budget
- Extra hours logged due to rework and debugging
- Higher than expected API service costs
IMPACT: At current CPI, the project will cost 1,956,955.00 PKR at completion,
exceeding the original budget by 230,230.00 PKR (13.3% overrun).
3. OVERALL PROJECT HEALTH
STATUS: PROJECT IS IN TROUBLE - Both schedule and cost are unfavorable.
COMBINED IMPACT:
- The project is behind schedule (SPI = 0.833)
- The project is over budget (CPI = 0.882)
- Both indices below 1.0 indicates poor performance on multiple fronts
CRITICAL CONCERNS:
✗ Schedule delays compound cost overruns (more time = more cost)
✗ Team velocity is 83.3% of planned - productivity issues
✗ Cost efficiency is 88.2% of planned - spending inefficiently
✗ Risk of missing December 21 deadline without corrective action
4. CORRECTIVE ACTIONS REQUIRED
IMMEDIATE ACTIONS:
1. Fast-track parallel activities where possible
2. Reduce scope if deadline is firm (descope non-critical features)
3. Add resources to critical path activities
4. Implement strict change control to prevent further delays
5. Increase daily standup frequency to weekly check-ins
COST CONTROL MEASURES:
1. Re-negotiate cloud service rates or switch to cheaper alternatives
2. Eliminate non-essential tooling
3. Reduce rework through better code reviews
4. Freeze scope - no new features
MONITORING:
1. Weekly EV analysis updates to track trends
2. Critical path activities must be monitored daily
3. Burndown charts for remaining work
4. Strict adherence to contingency reserve usage policies
5. FORECAST SUMMARY
Based on current trends:
ORIGINAL PLAN:
- Completion Date: December 21, 2025
- Total Budget: 1,726,725.00 PKR
CURRENT FORECAST (No Corrective Action):
- Completion Date: ~16 days late
- Total Cost: 1,956,955.00 PKR (13.3% over budget)
RECOMMENDATION: Implement aggressive corrective actions immediately or
request formal project baseline re-approval with revised schedule and budget.